## Project Overview
Product Owner | Meliha Ece Delier | B2280.060074 | Project Overwiev | Phase | Task Description | Primary Owner | Start Week | End Week | Status | Resource / Role | Weekly Hours | Hourly Rate | Total Weeks | Estimated Cost
Frontend Developer | Rümeysa Durdu | B2280.060059 | In The Unforeseen, our player portrays a medium. The medium's task is to enable their client to communicate with a deceased loved one by solving various puzzles. As the puzzles are solved, we witness the client's story and the medium's development. | Concept | Finalizing GDD & Story Arcs | Product Owner | Week 1 | Week 2 | To Do | Project Manager | 10 | $50 | 24 | $12,000
Backend Developer | Meliha Ece Delier | B2280.060074 |  | Planning | Resource Allocation & Risk Mapping | Project Manager | Week 1 | Week 2 | To Do | Product Owner | 8 | $45 | 24 | $8,640
Project Manager | Rümeysa Durdu | B2280.060059 |  | Backend | Database Schema & Puzzle Logic API | Backend Dev | Week 3 | Week 6 | To Do | Frontend Dev | 30 | $65 | 20 | $39,000
|  |  |  | Frontend | UI Wireframes & Environment Layout | Frontend Dev | Week 3 | Week 6 | To Do | Backend Dev | 30 | $65 | 20 | $39,000
|  |  |  | Core Dev | Implementing Mediumship Mechanics | Backend Dev | Week 7 | Week 12 | To Do | Software Licenses | Fixed | - | - | $1,500
|  |  |  | Core Dev | Visual Effects & Dialogue Systems | Frontend Dev | Week 7 | Week 12 | To Do | Marketing / Ads | Fixed | - | - | $5,000
|  |  |  | Integration | API Integration & Frontend Binding | Full Team | Week 13 | Week 16 | To Do | Contingency (10%) | - | - | - | $10,514
|  |  |  | Content | Narrative Assets & Client Story Entry | Product Owner | Week 14 | Week 18 | To Do | TOTAL BUDGET |  |  |  | $115,654
|  |  |  | QA | Bug Fixing & Performance Optimization | Project Manager | Week 19 | Week 22 | To Do
|  |  |  | Launch | Deployment & Final Polish | Project Manager | Week 23 | Week 24 | To Do