RISK ANALYSIS

The Unforeseen

1. Risk Identification and Evaluation

This section includes a detailed and game-specific risk table for The Unforeseen. Risks are categorized as:

- Game Mechanics (M)

- Project Management (P)

- Technical (T)

- Content/Quality (K)

### 1.1 Risk Assessment Table

| Risk ID | Risk Description | Probability | Impact | Level |
| --- | --- | --- | --- | --- |
| M-01 | Coffee cup shape recognition: The generated 3D cup model does not clearly reflect symbols (face, animal, object), making puzzles unsolvable. | High | High | High |
| M-02 | Palm reading zoom issue: Camera cannot properly focus or zoom on the hand due to collision or positioning issues. | Medium | High | High |
| M-03 | Incorrect star rendering: Procedural star system generates incorrect number or overlapping stars. | Medium | Medium | Medium |
| M-04 | Photo quality issue: In-game photos appear blurry or pixelated. | High | Medium | High |
| M-05 | Puzzle snapping issue: Pieces do not align or snap correctly. | Medium | High | High |
| M-06 | Dialogue branching error: Incorrect dialogue branch is triggered. | Low | High | Medium |
| M-07 | Scene transition freeze: Freezing during transitions between scenes. | Medium | Medium | Medium |
| M-08 | Player cannot understand puzzle logic (poor UX design): If the player cannot understand what to do, they may quit the game. | High | High | High |
| P-01 | Team member unavailability: Loss of a developer during sprint. | Medium | High | High |
| P-02 | Scope creep: Adding new puzzle types beyond scope. | High | Medium | High |
| P-03 | File conflicts: Version conflicts in Unity scenes. | Low | Critical | High |
| P-04 | Unity version mismatch: Different LTS versions cause incompatibility. | Medium | Medium | Medium |
| P-05 | Narrative inconsistency: Story conflicts between sprints. | Medium | Medium | Medium |
| P-06 | Poor task distribution: Some team members may be overloaded while others remain idle, causing imbalance in workload. | Medium | Medium | Medium |
| P-07 | Lack of communication between team members: Miscommunication can lead to incorrect implementations and time loss. | High | High | High |
| T-01 | Low FPS/performance issues: Game drops below 30 FPS. | Medium | High | High |
| T-02 | Build errors: Build fails due to dependencies or IL2CPP issues. | Low | High | Medium |
| T-03 | 3D asset import errors: Scale/UV issues in models. | High | Medium | High |
| T-04 | Save system corruption: Player progress data may become corrupted or lost. | Medium | Critical | High |
| T-05 | Memory leaks: Improper memory management may cause performance degradation or crashes during long gameplay sessions. | Medium | High | High |
| K-01 | Missing sound effects: Sounds not triggered correctly. | Medium | Low | Low |
| K-02 | Age rating issue: Content may exceed PEGI 7/12 limits. | Low | Medium | Medium |
| K-03 | UI/UX complexity: Menus and interface elements may be confusing or difficult to understand for players. | Medium | Medium | Medium |
| K-04 | Lack of player feedback (no hints, no guidance): Players may feel lost, bored, or frustrated and quit the game. | High | High | High |

## 1.2 Mitigation / Preventive Actions

| Risk ID | Mitigation / Preventive Actions |
| --- | --- |
| M-01 | Test the cup model with 5–10 different symbol variations before the scene starts; create a separate test scene for symbols. In case of failure, add an overlay hint system as a fallback. |
| M-02 | Prototype the zoom mechanism in an isolated test scene for the palm reading scene. Separate the camera collision layer; add smooth follow using Cinemachine. A playable demo is mandatory by the end of Sprint 2. |
| M-03 | Add minimum/maximum count parameters and debug logs to the star generator script. Write a unit test that asserts the star count before each build. |
| M-04 | Prepare all in-game photo textures with a minimum resolution of 512×512 px; lock the 'Max Texture Size' value to 1024 in import settings. Add this to the art guide document. |
| M-05 | Make the snap system tolerance radius adjustable; mark correct positions for each piece in the inspector. Make the puzzle mechanic fully playable in Sprint 2. |
| M-06 | Use a dialogue system based on Yarn Spinner or ScriptableObjects; track each branch transition using enum states. All branches are manually tested during sprint review. |
| M-07 | Load scene transitions using AsyncOperation; add a loading screen. All scene transitions are tested and recorded in every sprint. |
| M-08 | Provide clear visual and audio feedback, implement a hint system, and conduct user testing to ensure puzzles are understandable. |
| P-01 | Each developer learns core systems; all code is commented and the Trello backlog is kept up to date. Weekly Discord check-ins are mandatory. |
| P-02 | Apply MoSCoW prioritization at the start of each sprint; new feature requests are not accepted until the 'MUST' list is completed. The Product Owner manages scope control. |
| P-03 | All team members commit daily; Unity scenes are divided into prefabs to reduce merge conflicts. Large assets are protected using Git LFS or external backups. |
| P-04 | The Unity LTS version is documented in the README at the beginning of the project; all team members use the same version. .vsconfig is stored in a shared configuration repository. |
| P-05 | The scenario document is finalized during Sprint 1 retrospective; all dialogue decisions are recorded in the Game Design Document. |
| P-06 | Distribute tasks evenly during sprint planning, monitor workload regularly, and adjust assignments when necessary. |
| P-07 | Hold regular meetings (daily stand-ups), use communication tools (e.g., Discord, Trello), and ensure all decisions are documented. |
| T-01 | Run Unity Profiler in Sprints 2–3; add LOD groups, use baked lighting instead of real-time lighting. |
| T-02 | Take a test build for PC/Windows at the end of each sprint; include the build step in the sprint review checklist. |
| T-03 | Define FBX/OBJ import scale and UV settings in the art style guide; keep backups of source assets in the /Assets folder. |
| T-04 | Implement auto-save backups, validate save files before loading, and test the save/load system extensively. |
| T-05 | Use Unity Profiler to monitor memory usage, optimize asset management, and regularly test long play sessions. |
| K-01 | Create a sound checklist for each game event; assign a team member as sound responsible starting from Sprint 2. |
| K-02 | Review content (death, supernatural themes) according to PEGI 7/12 guidelines; avoid graphic depictions. |
| K-03 | Design simple and intuitive UI, follow UX principles, and conduct usability testing with players. |
| K-04 | Implement a hint system, provide visual/audio feedback, and guide players through subtle UI cues. |

## 1.3 Risk Matrix

| Probability / Impact | LOW Impact | MEDIUM Impact | HIGH Impact | CRITICAL Impact |
| --- | --- | --- | --- | --- |
| HIGH Probability |  | M-04, P-02, T-03 | M-01, M-05 |  |
| MEDIUM Probability | K-01 | M-03, M-07, P-04, P-05, T-01 | M-02, P-01, T-01 |  |
| LOW Probability |  | M-06, T-02, K-02 |  | P-03 |

# 2. Code Security and Data Privacy

## 2.1 Code Security

The Unforeseen is an offline, single-player PC game; it does not include a server component or an online multiplayer mode.

| Field | Applied Method |
| --- | --- |
| Source Code Protection | The repository is open for academic review; API keys or build credentials are never committed. UserSettings/ and local .env files are excluded via .gitignore. |
| Unity Build Security | C# assemblies are obfuscated if IL2CPP backend is used. Game logic is not written in plain text config files to prevent cheating. |
| Third-Party Assets | Unity Asset Store packages are reviewed for license compliance; only verified publishers' assets are used. |
| Version Control | GitHub access is managed via personal accounts; no shared credentials. All contributors must enable 2FA. |
| Dependency Management | Unity package versions are locked in Packages/manifest.json; packages are not auto-updated without team review. |

## 2.2 Data Privacy

Since the game has no network connection, user account system, or data collection mechanism, data privacy risk is minimal.

| Data Category | Status | Action |
| --- | --- | --- |
| Player Personal Data | Not collected | No registration, login, or telemetry system exists. |
| Save Files | Stored locally | Use Application.persistentDataPath; do not display file paths in UI. |
| Analytics / Telemetry | Not implemented | If added in the future, compliance with KVKK (Turkey) / GDPR is mandatory. |
| GitHub Commit Data | Name/username is public | Acceptable; commits do not contain sensitive data. |

# 3. Implementation Roadmap

## 3.1 Phase Overview

| Phase | Sprint | Date (Approx.) | Key Outputs |
| --- | --- | --- | --- |
| Phase 1: Pre-Production | Sprint 1 | Weeks 1–3 | Game Design Document, basic scene setup, character concept, dialogue system prototype |
| Phase 2: Core Development | Sprint 2 | Weeks 4–7 | Main puzzle mechanics (palm reading, puzzle), 3D environments (room, beach scenes), dialogue demo |
| Phase 3: Content & Polish | Sprint 3 | Weeks 8–11 | All puzzle types integrated, star/room scenes, SFX, UI polish, completed storyline |
| Phase 4: Testing & Release | Sprint Sonrası | Weeks 12–13 | QA testing, bug fixes, final build, GitHub release |

PROJECT MEMBERS

Meliha Ece Delier – B2280.060074

Rümeysa Durdu – B2280.060059